## TF-953A
A3 Template
Project name: | Reduction in downtime due to material shortages at WSA |  | Project Team: | Escalona Guzmán Erick David (TlP/TEF6), García Albarrán Daniela (TlP/TEF6), Muciño Esquivel Rubi (TlP/TEF6), Gonzalez Correa María de Lourdes (TlP/MSE-WS2) |  | Project Sponsor: | Gonzalez Correa María de Lourdes (TlP/MSE-WS2)
Project Owner: | Escalona Guzmán Erick David (TlP/TEF6), García Albarrán Daniela (TlP/TEF6) |  |  |  |  | CIP Coach: | Muciño Esquivel Rubi (TlP/TEF6)
[6 empty] | Date: | 2026-04-22
Background |  |  |  |  | Approach
Inicial State |  |  |  |  | Results
Target Condition |  |  |  |  | Metrics
Next Steps
© Robert Bosch México Sistemas Automotrices S.A. de C. V. se reserva todos los derechos. Prohibida su reproducción total o parcial. Ed/Sup: 2/1 = 19.Dic.25 TF-953A TI-204 C-SC1: interno
KPI Monitoring
Improvment
Downtime due to a shortage of materials in WSA
Ergonomic risk for Milkrun's Hc
No standardized PouP work
Fluctuation in the amount of material requested
122 min/month
Downtime due to material shortages
Without PoU Capacity
Undefined material highs and lows
Undefined route
Non dentified PoUs and stops
Undefined periodic and cyclical activities
Non PoUP Std Work
Non Process engineer training
PouP Standardized Work
1/10 production lines have PoUP standardized work
The 5 product lines with the highest materials demand should have PoUP standard work
Reduce downtime caused by material shortages by 15%
All standardized procedures in the PoUP should be understandable to operational staff
What?
Why?
How?
Reduce fluctuations in material requests
Increased Milkrun cycle time and ergonomic risks
-Standardize the procedure for requesting materials
Reduce downtime caused by by material shortages
Costs due to downtime
-Root cause analysis
-Analysis of Material Requests
PouP Standardrized Work
Responsible for the procurement and requesting materials
-Cycle time and activities analysis
-Identify Point of Use
-Material Analysis
96 min/month
Downtime due to material shortages
5/10 production lines have PoUP standardized work
Reduction of 21 % min
PoU capacity
Defined material highs and lows
Defined route
Defined PoUP and stops
Defined periodic and cyclical activities
PoUP standardized work
Process engineering training
PouP Standardized Work
Standardize the remaining 5 lines to achieve 100% standardization of PouP tasks in WSA

## Sheet1
Yes | 1
No

## Registro de Cambios (TF-953A)
Registro de cambios de TF-953A
Versión | Descripción del cambio | Fecha | Autor
2/0 | Actualización de fecha | 31.Ene.2022 | BPS
2/1 | Se actualiza la estructura del formato, se cambian los logos BPS y se agrega pie de pagina | 19.Dic.2025 | TlP/BPS J Plata